[AI-Based Reviewer on Project Code and Architecture] - Project Plan Template

System Name:[AI-Based Reviewer on Project Code and Architecture]
Prepared by: [BaiXuan Zhang] 
Project Advisor: [Dr. Siraprapa Wattanakul] 
Date: [Date]

目录

[AI-Based Reviewer on Project Code and Architecture] - Project Plan Template	1

1. Introduction	2

1.1 Purpose	2

1.2 Project Overview	2

1.3 Project Scope	3

2. Project Deliverables (Work Products)	6

2.1 Documentation Deliverables	6

2.2 Software Deliverables	8

3. Project Organization and Management	9

3.1 Project Team and Roles	9

3.2 Work Breakdown Structure (WBS)	11

3.3 Monitoring and Controlling	14

3.4 Communication Management	16

3.5 Risk Management	18

3.6 Change Management	20

3.7 Procurement and Vendor Management	22

3.8 Stakeholder Management	23

3.9 Project Closure Procedures	24

4. Quality Standards	26

4.1 Applicable Standards and Frameworks	26

4.2 Quality Objectives and Metrics	26

4.3 Quality Assurance (QA) Activities	27

4.4 Quality Control — Code Quality Gates	28

4.5 Defect Management	28

5. Software Configuration Management	30

5.1 Naming Conventions	30

5.2 Project Repository	30

5.3 Branch Strategy (Source Code)	31

5.4 Document Control	31

6. Project Schedule and Milestones	32

6.1 Detailed Project Schedule by Phase	32

6.2 Major Milestones and Go/No-Go Criteria	32

6.3 Resource Acquisition Timeline	34

6.4 Budget Summary	35

1. Introduction

1.1 Purpose

This Project Management Plan (PMP) defines the comprehensive management approach for the AI-Based Reviewer project. It covers all planning, execution, monitoring, controlling, and closing activities from project initiation through final delivery.

This document serves as the authoritative guide for project governance — establishing how decisions are made, how work is organized, how risks and changes are managed, and how quality is ensured. All project team members and stakeholders should refer to this document to understand their responsibilities and the project's operating procedures.

1.2 Project Overview

- The AI-Based Reviewer is an intelligent, web-based platform that automates code review and architectural analysis for software development projects. Instead of relying entirely on human reviewers — a process that is slow, inconsistent, and expensive — the system uses artificial intelligence to analyze code and provide structured, actionable feedback automatically.

- The platform works by integrating three core technologies:

- ·Abstract Syntax Trees (AST): a technique that converts source code into a structured tree representation, allowing the system to understand code structure rather than just reading it as plain text.

- ·Neo4j Graph Database: a specialized database that stores relationships between code components (functions, modules, imports), enabling analysis of how different parts of the codebase depend on one another.

- ·Large Language Models (LLMs): AI models (GPT-4 and Claude) that read the parsed code and generate human-readable, context-aware feedback, similar to what an experienced senior developer would write.

- The system provides the following key capabilities:

- ·Automated pull request (PR) code review with AI-powered feedback — developers receive inline comments directly on their GitHub PRs within minutes, requiring no manual reviewer action.

- ·Real-time architectural drift detection — the system identifies when the codebase deviates from its intended structure (e.g., unexpected circular dependencies or cross-layer calls).

- ·Interactive dependency graph visualization — engineers can visually explore how modules relate to each other.

- ·Enterprise-grade authentication with Role-Based Access Control (RBAC) and a full audit log for accountability.

- Target Users: Software developers, code reviewers, engineering managers, and software architects.

- Deployment Model: Cloud-based Software-as-a-Service (SaaS) hosted on Amazon Web Services (AWS) infrastructure.

1.3 Project Scope

- This section defines what is included in the project and what is explicitly excluded, ensuring all stakeholders share the same understanding of project boundaries.

1.3.1 In Scope — Core Features

- Feature #1: AI Code Review — Automated PR Analysis with LLM Integration

- How users experience it: A developer opens a pull request on GitHub. Without any manual action, the system automatically receives the PR event via a webhook, triggers an analysis pipeline, and posts structured review comments directly on the PR within minutes.

- How it works technically: The system parses the changed source files into Abstract Syntax Trees to extract structural code information. These trees are passed to a Large Language Model, which evaluates code quality, logic correctness, security vulnerabilities, naming conventions, and adherence to best practices. Review results are mapped back to specific lines in the code diff.

- What the user sees: Inline GitHub PR comments with severity labels (Critical / Warning / Suggestion), a summary review report per PR with an overall quality score, and a breakdown by category (security, maintainability, coding style).

- Feature #2: Graph-Based Architecture Analysis — Neo4j Dependency Tracking

- How users experience it: An engineering manager or architect opens the Architecture Analysis module, selects a repository, and triggers an analysis. They can then explore an interactive dependency graph, filter by module or layer, and inspect flagged violations with drill-down detail.

- How it works technically: The system parses the codebase to extract inter-module dependencies, function call chains, and import relationships. These are stored as a property graph in Neo4j. Graph algorithms then detect architectural drift — deviations from the intended layered or modular structure — by comparing the current dependency graph against a defined baseline. Circular dependencies, unexpected cross-layer calls, and high-coupling clusters are automatically flagged.

- What the user sees: An interactive graph visualization (zoom, pan, filter by node type), a drift report listing all detected violations with affected nodes and recommended remediation, and trend charts showing architectural health over time.

- Feature #3: Authentication System — Enterprise Security

- How users experience it: Users register or log in via the web portal using email/password or Single Sign-On (SSO). Administrators access a Management panel to assign roles and configure permissions per project. All session activity is visible in the audit log dashboard.

- How it works technically: The system implements JSON Web Token (JWT)-based session management with refresh token rotation, enforced at both API and UI levels. Rate limiting and brute-force protection guard against unauthorized access. All authentication events are captured in an immutable audit log for compliance traceability. Role-Based Access Control (RBAC) ensures users can only access resources appropriate to their role.

- What the user sees: Secure session tokens, a role and permission management interface, and a paginated audit log exportable as CSV.

- Feature #4: Project Management — Repository and Analysis Lifecycle Management

- How users experience it: A user connects their GitHub account, imports one or more repositories, and configures analysis settings (e.g., target branches, review sensitivity, notification preferences). They can view historical analysis runs, compare results across versions, and manage team access per project.

- How it works technically: The module supports multi-repository management with per-project configuration, GitHub OAuth integration for repository import, webhook lifecycle management (register, pause, delete), and analysis history with version diffing. Project-level dashboards aggregate key metrics across all analysis types.

- What the user sees: A project dashboard showing analysis run history, status indicators, and aggregated quality trends; configuration pages for webhook and review settings; and team membership management.

1.3.2 Out of Scope (Version 1.0)

- The following are explicitly not included in this project and will be considered for future versions:

- Mobile native applications (iOS or Android) — the system is web-browser-based only.

- On-premise deployment — the system is cloud-hosted (AWS) only; no self-hosting option.

- GitLab or Bitbucket integration — only GitHub is supported in v1.0.

- Multi-language user interface — English only in v1.0.

- Real-time collaborative editing or pair-review sessions.

- Custom LLM model training on proprietary codebases.

1.3.3 Project Constraints

| - Constraint | - Details |
| --- | --- |
| - Budget | - $63,500 development cost + $19,880/year operational cost |
| - Timeline | - 24 weeks (6 months) from project kickoff to closure |
| - Team Size | - 1 developer (BaiXuan Zhang) fulfilling multiple roles, supervised by 1 advisor (Dr. Siraprapa Wattanakul) |
| - Technology Stack | - Python (FastAPI), React/Next.js, PostgreSQL, Neo4j, Redis, AWS |
| - Standards | - ISO/IEC 29110, IEEE 1058, ISO 21500, ISO/IEC 25010, OWASP Top 10 |

2. Project Deliverables (Work Products)

This section lists all documents and software artifacts that must be produced and submitted during the project lifecycle. Deliverables are divided into documentation deliverables and software deliverables.

2.1 Documentation Deliverables

The following documents must be produced in accordance with the project's SDLC and academic requirements:

| Deliverable | Description | Due | Owner | Reviewer |
| --- | --- | --- | --- | --- |
| Project Proposal | Business case, feasibility analysis, stakeholder analysis, and initial project justification. | Week 2 | BaiXuan Zhang | Dr. Siraprapa |
| Project Management Plan (PMP) | This document — comprehensive plan covering scope, schedule, resources, quality, risk, communication, and change management. | Week 4 | BaiXuan Zhang | Dr. Siraprapa |
| Software Requirements Specification (SRS) | Functional and non-functional requirements — what the system must do and how well it must do it. | Week 6 | BaiXuan Zhang | Dr. Siraprapa |
| Software Design Document (SDD) | System architecture, database schema design, API design, security design, and UI/UX design. | Week 8 | BaiXuan Zhang | Dr. Siraprapa |
| Software Test Plan | Test strategy, test cases, test environment setup, and acceptance criteria for each feature. | Week 18 | BaiXuan Zhang | Dr. Siraprapa |
| Software Test Record | Actual test execution results, defect reports, and test evidence for all test cases. | Week 20 | BaiXuan Zhang | Dr. Siraprapa |
| Traceability Record | Requirements-to-tests traceability matrix mapping each requirement to its test case(s). | Week 20 | BaiXuan Zhang | Dr. Siraprapa |
| Change Request (CR) Log | Record of all submitted change requests, their impact analysis, approval decisions, and implementation status. | Ongoing | BaiXuan Zhang | Dr. Siraprapa |
| User Guide | End-user documentation explaining how to install, configure, and use the AI-Based Reviewer platform. | Week 22 | BaiXuan Zhang | Dr. Siraprapa |
| API Documentation | Developer API reference documented in OpenAPI (Swagger) specification format. | Week 22 | BaiXuan Zhang | Dr. Siraprapa |
| Deployment Guide | Infrastructure setup instructions and step-by-step deployment procedures for staging and production environments. | Week 22 | BaiXuan Zhang | Dr. Siraprapa |
| Final Project Report | Project summary, outcomes vs. objectives, lessons learned, and recommendations for future development. | Week 24 | BaiXuan Zhang | Dr. Siraprapa |

2.2 Software Deliverables

The following software components must be developed, tested, and deployed:

| Deliverable | Description | Due | Acceptance Criteria |
| --- | --- | --- | --- |
| Database Schema | PostgreSQL relational schema + Neo4j graph model | Week 10 | Schema validated, all migrations tested successfully |
| Authentication System | JWT-based login, refresh token rotation, RBAC authorization | Week 12 | All 36 RBAC properties pass property-based tests (100 iterations) |
| GitHub Integration | Webhook handler + GitHub API client for PR event processing | Week 14 | PR review workflow end-to-end functional |
| LLM Integration | GPT-4 + Claude API integration with prompt templates, rate limiting, and fallback logic | Week 14 | Code analysis generates actionable feedback; rate limiting works; fallback to secondary model functional |
| Graph Analysis Engine | Neo4j dependency analysis and circular dependency detection | Week 15 | Circular dependency detection functional; drift reports generated correctly |
| Backend API | FastAPI REST services for all platform features | Week 16 | All API endpoints functional, >80% test coverage |
| Frontend Application | React/Next.js web UI with dashboard and all analysis result views | Week 16 | All UI components functional, responsive design, all charts render correctly |
| Deployment Package | Docker containers + Kubernetes (K8s) manifests for staging and production | Week 22 | Successful automated deployment to both staging and production environments |
| Source Code Repository | Complete codebase with full version history, documentation, and CI/CD pipelines | Week 24 | All code committed, documented, peer-reviewed, and archived |

3. Project Organization and Management

This section describes how the project is organized and governed, including team structure, work breakdown, monitoring, communication, risk management, change control, procurement, and project closure.

3.1 Project Team and Roles

This project is a single-developer academic project. BaiXuan Zhang serves in all technical and management roles under the supervision of Dr. Siraprapa Wattanakul, who acts as Project Sponsor and advisor.

3.1.1 Organization Structure

Project Sponsor: Dr. Siraprapa Wattanakul

└─ Project Manager / Technical Lead: BaiXuan Zhang

├─ Backend Developer (BaiXuan Zhang)

├─ Frontend Developer (BaiXuan Zhang)

├─ QA Engineer (BaiXuan Zhang)

└─ DevOps Engineer (BaiXuan Zhang)

3.1.2 Team Member Profiles

| Role | Name | Allocation | Key Skills | Responsibilities |
| --- | --- | --- | --- | --- |
| Project Sponsor | Dr. Siraprapa Wattanakul | 5% | Project management, academic oversight | Strategic direction, resource approval, milestone reviews and sign-offs |
| Project Manager | BaiXuan Zhang | 20% | Planning, coordination, risk management | Overall delivery, stakeholder management, reporting |
| Backend Developer | BaiXuan Zhang | 50% | Python, FastAPI, PostgreSQL, Neo4j | API development, database design, LLM integration |
| Frontend Developer | BaiXuan Zhang | 20% | React, Next.js, TypeScript, D3.js | UI development, dashboard, graph visualization |
| QA Engineer | BaiXuan Zhang | 15% | pytest, Jest, test automation | Test planning, execution, quality assurance |
| DevOps Engineer | BaiXuan Zhang | 10% | AWS, Docker, Kubernetes, CI/CD | Infrastructure setup, deployment pipelines, monitoring |

Note: Total allocation is 120%, reflecting overlapping activities and multitasking across roles.

3.1.3 RACI Responsibility Matrix

The RACI matrix defines who is Responsible (R), Accountable (A), Consulted (C), or Informed (I) for each major project activity. Each activity must have exactly one Accountable party.

| Activity | Sponsor | Proj. Mgr. | Developer | QA | DevOps |
| --- | --- | --- | --- | --- | --- |
| Project Planning | A | R | C | I | I |
| Requirements Analysis | C | R/A | R | C | I |
| System Design | C | R/A | R | C | C |
| Development | I | A | R | I | I |
| Unit Testing | I | A | R | R | I |
| Integration Testing | I | A | R | R | C |
| System Testing | C | A | C | R | C |
| Deployment | C | A | C | I | R |
| Documentation | C | A | R | C | I |
| Project Closure | A | R | C | I | I |

Legend: R = Responsible (does the work), A = Accountable (owns the outcome), C = Consulted (input required), I = Informed (kept updated)

3.1.4 Decision-Making Authority

| Decision Type | Authority | Escalation Path |
| --- | --- | --- |
| Technical design choices | Project Manager | Project Sponsor (if budget/schedule impact) |
| Requirement changes | Project Sponsor | N/A (final authority) |
| Schedule adjustments (< 1 week) | Project Manager | Project Sponsor for awareness |
| Schedule adjustments (≥ 1 week) | Project Sponsor | University Administration |
| Budget changes (< 10%) | Project Manager | Project Sponsor for approval |
| Budget changes (≥ 10%) | Project Sponsor | University Administration |
| Quality standards | Project Manager | Project Sponsor (if conflicts arise) |
| Risk response strategies | Project Manager | Project Sponsor for high-impact risks |

3.2 Work Breakdown Structure (WBS)

The Work Breakdown Structure decomposes the total project scope into manageable work packages. Each work package is small enough to estimate, assign, and track. This WBS follows a phase-based Level 1 structure with deliverable-based Level 2 breakdown.

3.2.1 WBS Hierarchy

| Phase ID | Phase Name & Timing | Major Work Packages |
| --- | --- | --- |
| Phase 1 | Project Initiation (Week 1-2) | 1.1 Project Charter ¦ 1.2 Stakeholder Analysis ¦ 1.3 Risk Register ¦ 1.4 Development Environment Setup |
| Phase 2 | Requirements & Design (Week 3-8) | 2.1 URS ¦ 2.2 SRS ¦ 2.3 NFR ¦ 2.4 Architecture Design ¦ 2.5 Database Schema Design ¦ 2.6 API Design ¦ 2.7 Security Design ¦ 2.8 UI/UX Design |
| Phase 3 | Development (Week 9-16) | 3.1 Auth System ¦ 3.2 RBAC Authorization ¦ 3.3 Project Mgmt APIs ¦ 3.4 GitHub Integration ¦ 3.5 AST Parser ¦ 3.6 LLM Integration ¦ 3.7 Graph Analysis Engine ¦ 3.8 Audit Logging ¦ 3.9 Frontend UI ¦ 3.10 Graph Visualization |
| Phase 4 | Testing & QA (Week 17-20) | 4.1 Unit Testing ¦ 4.2 Integration Testing ¦ 4.3 System Testing ¦ 4.4 Security Testing ¦ 4.5 Performance Testing ¦ 4.6 User Acceptance Testing |
| Phase 5 | Deployment & Documentation (Week 21-22) | 5.1 Infrastructure Setup ¦ 5.2 Staging Deployment ¦ 5.3 Production Deployment ¦ 5.4 User Docs ¦ 5.5 API Docs ¦ 5.6 Operations Guide |
| Phase 6 | Project Closure (Week 23-24) | 6.1 Final Testing & Validation ¦ 6.2 Stakeholder Acceptance ¦ 6.3 Knowledge Transfer ¦ 6.4 Lessons Learned ¦ 6.5 Project Archive |

3.2.2 Sample Work Package Definitions

Each work package includes the following attributes to enable accurate planning and tracking:

| Work Package | Details |
| --- | --- |
| ID: 3.1 — Authentication System | Description: Implement JWT-based login with bcrypt password hashing, refresh token rotation, and rate limiting. Deliverables: auth_service.py, JWT middleware, password hashing utilities. Duration: 40 hours (1 week) ¦ Dependencies: Database schema (2.5) Resources: Backend Developer ¦ Acceptance Criteria: All 12 unit tests pass; property-based tests pass (100 iterations) |
| ID: 3.6 — LLM Integration | Description: Integrate GPT-4 and Claude 3.5 APIs for automated code analysis, with prompt templates, Redis-based rate limiting, and fallback logic. Deliverables: llm_service.py, prompt templates, rate limiting module, fallback handler. Duration: 60 hours (1.5 weeks) ¦ Dependencies: AST Parser (3.5), Graph Analysis (3.7) Resources: Backend Developer ¦ Acceptance Criteria: Code analysis generates actionable feedback; rate limiting works; fallback to secondary model functional |

3.2.3 Critical Path Analysis

The critical path is the longest chain of dependent tasks. Any delay on the critical path directly delays the project end date.

Critical Path (in order):

| # | Activity | Timing | Why Critical |
| --- | --- | --- | --- |
| 1 | Requirements Gathering & Approval | Week 3-6 | All downstream design and dev depends on approved requirements |
| 2 | Database Schema Design & Implementation | Week 7-8 | Backend services cannot be built without a working database schema |
| 3 | Backend API Core Development | Week 9-12 | Auth, APIs, and core services are prerequisites for all integrations |
| 4 | LLM and Graph Analysis Integration | Week 13-14 | Core differentiating features; required before frontend can be fully built |
| 5 | Frontend Integration & Full Feature Completion | Week 15-16 | Must be complete before end-to-end system testing begins |
| 6 | End-to-End System Testing | Week 17-18 | All issues must be resolved before deployment approval |
| 7 | Production Deployment | Week 21-22 | Final deliverable; must succeed before project closure |

Total Critical Path Duration: 20 weeks

Project Buffer: 4 weeks (20% of critical path, built in for risk absorption)

Total Project Duration: 24 weeks

3.3 Monitoring and Controlling

Monitoring and controlling activities ensure the project stays on track with respect to schedule, budget, quality, and scope. Deviations are detected early and corrective actions are taken before they escalate into major problems.

3.3.1 Software Development Life Cycle (SDLC) Model

This project follows an Iterative and Incremental development model with elements of Agile methodology. Each two-week sprint produces working, testable software increments. This approach allows early feedback, reduces integration risk, and provides flexibility to adapt to new information.

3.3.2 Key Performance Indicators (KPIs)

| KPI | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| Schedule Performance Index (SPI) | ≥ 0.95 | Earned Value Management (EVM) calculation | Monthly |
| Cost Performance Index (CPI) | ≥ 0.95 | EVM calculation | Monthly |
| Requirements Completion | 100% Must-Have | Traceability matrix review | Per milestone |
| Code Coverage | > 80% critical | pytest-cov / Jest coverage reports | Per sprint |
| Defect Density | < 5 per 1000 LOC | Defect tracking log | Per milestone |
| Test Pass Rate | > 95% | Test execution results | Per test cycle |
| Stakeholder Satisfaction | > 4.0 / 5.0 | Post-deployment survey | End of project |

3.3.3 Progress Tracking

Weekly Progress Tracking (every Friday):

Tasks completed vs. planned for the week

Schedule variance — are we ahead, on track, or behind?

Budget variance — are we spending within the planned budget?

Active risk and issue status

Blockers and unresolved dependencies

Monthly Progress Review:

Overall milestone progress and go/no-go assessment

EVM metrics (SPI, CPI) calculated and reported to Project Sponsor

Quality metrics review (test coverage, defect density, pass rates)

Stakeholder feedback collection and response

Corrective actions identified and assigned

3.3.4 Issue Management

All issues are logged in the GitHub Issues tracker and follow this lifecycle: Identification → Categorization (technical, resource, schedule, scope) → Prioritization (P0–P3) → Assignment → Resolution → Verification → Closure.

Issue escalation thresholds:

P0 (Critical): Immediate escalation to Sponsor — examples: production outage, data loss, security breach

P1 (High): Escalate if not resolved within 3 days — examples: major feature broken, integration failure

P2 (Medium): Escalate if not resolved within 1 week — examples: functionality impaired with workaround

P3 (Low): Escalate if not resolved within 2 weeks — examples: cosmetic issues, minor documentation gaps

Earned Value Management (EVM) — the project uses EVM to objectively measure progress:

Planned Value (PV): The budgeted cost of work scheduled at any given point

Earned Value (EV): The budgeted cost of work actually completed

Actual Cost (AC): The real cost incurred to date

Schedule Variance (SV) = EV - PV. A positive value means ahead of schedule.

Cost Variance (CV) = EV - AC. A positive value means under budget.

SPI = EV/PV; CPI = EV/AC. Values above 1.0 are healthy.

3.4 Communication Management

Effective communication ensures all stakeholders remain informed, decisions are made at the right level, and issues are surfaced early.

3.4.1 Stakeholder Communication Matrix

| Stakeholder | Information Needs | Communication Method | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Project Sponsor (Dr. Siraprapa) | Progress, risks, decisions, budget status | Face-to-face meeting + written status report | Weekly | Project Manager |
| Project Manager (BaiXuan Zhang) | All project information | Self-tracking (daily log, GitHub, task board) | Daily | Self |
| University Administration | Milestone completion, final results | Formal written report + presentation | Per semester | Project Sponsor |
| End Users (Developers) | Feature updates, usage tips, support | Email newsletter, release notes | Bi-weekly (post-launch) | Project Manager |
| Peer Reviewers | Code changes, design decisions | GitHub Pull Request comments | Per PR | Developer |

3.4.2 Meeting Schedule

| Meeting | Purpose | Frequency | Duration | Participants & Agenda |
| --- | --- | --- | --- | --- |
| Project Kickoff | Align on goals, roles, schedule, and expectations before work begins | Once (Week 1) | 2 hours | PM + Sponsor ¦ Overview, roles, schedule, expectations |
| Weekly Status Meeting | Review progress, resolve issues, plan the upcoming week | Every Friday 2-3 PM | 1 hour | PM + Sponsor ¦ Status, risks, decisions, next week plan |
| Milestone Review | Formal acceptance of milestone deliverables and go/no-go for next phase | 8 times (per milestone) | 2 hours | PM + Sponsor ¦ Deliverable review, criteria check, go/no-go |
| Design Review | Validate technical architecture, database, API, and security design before development begins | Once (Week 8) | 2 hours | PM + Sponsor ¦ Architecture, database, API, security |
| Sprint Planning | Plan the sprint backlog and break down tasks for the next 2 weeks | Bi-weekly | 1 hour | PM (self) ¦ Sprint backlog, task breakdown |
| Sprint Retrospective | Identify what went well, what to improve, and action items for the next sprint | Bi-weekly | 30 min | PM (self) ¦ Successes, improvements, actions |
| Project Closure | Final deliverables review, sign-off, lessons learned, and project handover | Once (Week 24) | 2 hours | PM + Sponsor ¦ Final review, lessons, sign-off |

3.4.3 Communication Channels

| Channel | Purpose | Participants | Expected Response Time |
| --- | --- | --- | --- |
| Weekly Status Meeting | Progress review, issue resolution, decision-making | PM + Sponsor | N/A (scheduled) |
| Email | Formal communication, decisions, milestone reports | All stakeholders | Within 24 hours |
| GitHub Issues | Bug tracking, feature requests, technical backlog management | Development team | Within 48 hours |
| GitHub Pull Requests | Code review, technical discussion, merge approvals | Development team | Within 24 hours |
| Slack / Discord | Quick questions, informal updates, daily check-ins | Development team | Within 4 hours |
| Project Documentation | Formal deliverables, specifications, guides | All stakeholders | N/A (reference) |

3.5 Risk Management

Risk management follows ISO 31000 principles: Identification → Analysis → Evaluation → Treatment → Monitoring. Risks are scored using the formula: Risk Score = Probability (as a decimal) × Impact (1–5 scale). Risks scoring ≥ 1.0 are classified as high priority and require explicit mitigation plans.

3.5.1 Risk Register

| ID | Risk Description | Category | Probability | Impact | Score | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | LLM API rate limiting causes processing delays and degraded user experience | Technical | Medium (40%) | High (4) | 1.6 | PM |
| R-004 | LLM API costs exceed the planned budget due to higher-than-expected usage | Financial | Medium (50%) | Medium (3) | 1.5 | PM |
| R-009 | Schedule delay due to underestimated technical complexity of LLM/graph integration | Schedule | Medium (35%) | High (4) | 1.4 | PM |
| R-010 | Scope creep from new stakeholder requests not in the original SRS | Scope | Medium (40%) | Medium (3) | 1.2 | PM |
| R-005 | Lower-than-expected user adoption after launch | Operational | Medium (30%) | High (4) | 1.2 | PM |
| R-007 | Key team member (BaiXuan) unavailable due to illness or personal emergency | Resource | Low (15%) | High (4) | 0.6 | Sponsor |
| R-002 | Neo4j graph database performance degrades with large codebases (>500K LOC) | Technical | Low (20%) | High (4) | 0.8 | PM |
| R-006 | Security vulnerability discovered in authentication or data handling | Security | Low (10%) | Critical (5) | 0.5 | PM |
| R-003 | GitHub API changes break existing webhook integration | Technical | Low (15%) | Medium (3) | 0.45 | PM |
| R-008 | Regulatory compliance requirements change mid-project | Regulatory | Low (20%) | Medium (3) | 0.6 | PM |

Highlighted scores (≥ 1.0) are High Priority risks requiring explicit mitigation plans. Score = Probability × Impact.

3.5.2 Risk Response Strategies (High Priority)

| Risk | Risk Description | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- |
| R-001 | LLM API rate limiting | Implement Redis-based request queue with exponential backoff; use multiple API keys for distribution. Implement in Week 13. | Fall back to secondary LLM provider (Claude API); reduce analysis frequency during peak demand. |
| R-004 | LLM API cost overrun | Real-time cost monitoring dashboard with $1,000/month spending cap; optimize prompt length; implement response caching. Implement in Week 1. | Reduce analysis frequency; implement aggressive caching; switch to cheaper model tiers. |
| R-009 | Schedule delay | 4-week buffer (20%) built into project timeline; weekly progress tracking against plan; early identification via critical path monitoring. | Reduce scope to Must-Have only; defer Should-Have features to v2.0; request timeline extension with sponsor approval. |
| R-010 | Scope creep | Formal change control process; clear scope baseline documented in SRS; stakeholder education on change request process. | Defer all new requests to v2.0 roadmap; negotiate timeline extension only for critical changes. |
| R-005 | Low user adoption | 4-week pilot with 5 early adopters pre-launch; feedback-driven feature iterations; comprehensive onboarding documentation. | Extended pilot phase; feature adjustments based on feedback; marketing outreach to developer communities. |

3.5.3 Risk Monitoring

Risk review is conducted at every weekly status meeting. Risk scores are recalculated based on current information. Escalation is triggered when a risk score increases to ≥ 2.0, a mitigation strategy fails, a new critical risk is identified, or multiple risks materialize simultaneously.

3.6 Change Management

All changes to project scope, schedule, budget, or quality standards must follow a formal change control process. This prevents uncontrolled scope expansion and ensures all changes are evaluated for impact before implementation.

3.6.1 Change Control Process (Step by Step)

Change Request Submission: The requester completes a Change Request (CR) form describing the requested change, the business justification, expected impact, and priority. The CR is submitted to the Project Manager.

Impact Analysis: The Project Manager analyzes the impact on requirements, design, code, tests, schedule, budget, resources, quality, and stakeholders. The impact analysis is documented in the CR form.

Change Control Board (CCB) Review: The CCB (Project Sponsor as Chair, Project Manager, QA Lead) meets weekly to review pending CRs. The CCB evaluates business value, technical feasibility, impact, and priority. Decision options: Approve / Reject / Defer / Approve with Conditions.

Implementation (if Approved): The Project Manager assigns the CR to the responsible party. Implementation is tracked in the CR form. Testing and verification are performed. Documentation is updated to reflect the change.

Closure: Implementation is verified and validated. Stakeholders are notified. The CR is closed with lessons learned recorded. The traceability matrix is updated to reflect any requirement changes.

3.6.2 Change Categories and Approval Authority

| Change Type | Examples | Approval Authority | Timeline |
| --- | --- | --- | --- |
| Minor Change | Bug fixes, documentation updates, minor UI tweaks with no scope impact | Project Manager alone | 1-2 business days |
| Moderate Change | New Should-Have feature, design modifications, API endpoint changes | CCB (Sponsor + PM + QA Lead) | 1 week |
| Major Change | Scope change, architecture overhaul, new Must-Have requirement | CCB + Project Sponsor final approval | 2 weeks |
| Critical / Emergency | Security vulnerability patch, production outage fix, compliance-driven change | Emergency approval (PM + Sponsor via phone/email) | Within 24 hours |

3.6.3 Change Control Board (CCB) Composition

| Role | Name | Responsibility |
| --- | --- | --- |
| CCB Chair | Dr. Siraprapa Wattanakul | Final approval authority; strategic alignment with academic and organizational goals |
| Technical Lead | BaiXuan Zhang | Technical feasibility assessment, effort estimation, impact analysis on codebase |
| QA Lead | BaiXuan Zhang | Quality and testing impact assessment; ensures changes do not compromise test coverage |

CCB Meeting Schedule: Weekly on Fridays, 2:00–3:00 PM (can be combined with the weekly status meeting).

3.6.4 Project Baselines

Any change to a baseline requires CCB approval and triggers a full impact analysis:

Scope Baseline: Approved SRS document (Week 6)

Schedule Baseline: Approved project schedule (Week 4, i.e., this document)

Cost Baseline: Approved project budget (Week 4, i.e., this document)

3.7 Procurement and Vendor Management

3.7.1 Procurement Requirements

| Item | Vendor | Procurement Method | Timeline | Estimated Cost |
| --- | --- | --- | --- | --- |
| OpenAI GPT-4 API | OpenAI | Online signup with credit card; pay-per-use billing | Week 1 | $6,000 |
| Anthropic Claude API | Anthropic | Online signup with credit card; pay-per-use billing | Week 1 | $2,000 |
| AWS Cloud Services | Amazon Web Services | Online signup; pay-as-you-go pricing | Week 8 | $2,320 |
| Neo4j AuraDB | Neo4j | Online signup; trial then paid subscription | Week 8 | $520 |
| GitHub | GitHub (Microsoft) | Online signup; free tier | Week 1 | $0 |

3.7.2 License Compliance

| Component | License | Commercial Use | Attribution Required | Compliance Action |
| --- | --- | --- | --- | --- |
| FastAPI | MIT | Yes | Yes | Include in NOTICE file |
| React | MIT | Yes | Yes | Include in NOTICE file |
| PostgreSQL | PostgreSQL License | Yes | No | No additional action required |
| Neo4j AuraDB | Commercial | Yes (paid tier) | N/A | Maintain active subscription |
| OpenAI API | Commercial ToS | Yes | N/A | Comply with OpenAI Terms of Service |

3.8 Stakeholder Management

| Stakeholder | Role | Interest | Influence | Engagement Strategy |
| --- | --- | --- | --- | --- |
| Dr. Siraprapa Wattanakul | Project Sponsor | High | High | Manage Closely — weekly meetings, milestone reviews, all major decisions |
| BaiXuan Zhang | PM / Developer | High | High | Self-management — daily tracking, weekly planning, sprint retrospectives |
| University Administration | Oversight | Medium | High | Keep Satisfied — semester progress reports, final presentation |
| End Users (Developers) | Beneficiaries | High | Low | Keep Informed — beta testing invitations, feedback surveys, release notes |
| IT Operations | Infrastructure | Low | Medium | Monitor — deployment notifications, handover documentation |

3.9 Project Closure Procedures

Project closure is initiated when ALL of the following criteria are confirmed to be met. Early closure without meeting all criteria is not permitted.

3.9.1 Closure Criteria

Deliverables Complete:

All planned documentation deliverables completed, reviewed, and accepted by Project Sponsor

All software deliverables deployed and verified in production

Source code committed, documented, and archived in repository

Quality Standards Met:

100% of Must-Have requirements implemented and verified against acceptance criteria

All Critical and High-priority defects resolved

Code coverage >80% for all critical components

Security audit completed with zero critical or high-severity vulnerabilities

Stakeholder Acceptance:

Project Sponsor formal written acceptance obtained

User Acceptance Testing (UAT) completed successfully

Final presentation delivered and approved by academic committee

Administrative Closure:

All vendor contracts and procurement commitments closed

Final budget reconciliation completed and documented

All project team members formally released from project duties

Project archive completed and stored in designated location

3.9.2 Closure Activity Schedule

| Activity | Description | Responsible | Timing |
| --- | --- | --- | --- |
| Final Testing & Bug Fixing | Complete all remaining test cases; fix all remaining critical and high-priority defects | QA Engineer | Week 23 |
| Documentation Review | Review and finalize all project documents; ensure version consistency and completeness | Project Manager | Week 23 |
| Stakeholder Acceptance | Obtain formal written acceptance from Project Sponsor on all deliverables | Project Manager | Week 23 |
| Knowledge Transfer | Transfer system knowledge, deployment procedures, and support contacts to university IT team | Project Manager | Week 24 |
| Lessons Learned Session | Conduct retrospective with PM and Sponsor: what went well, what to improve, insights, recommendations | Project Manager | Week 24 |
| Project Archive | Archive all project artifacts (documents, code, test results, minutes, CRs) in repository and Google Drive | Project Manager | Week 24 |
| Final Report Submission | Prepare and submit the Final Project Report including summary, outcomes, lessons learned, and recommendations | Project Manager | Week 24 |

3.9.3 Post-Project Support

Warranty Period: 3 months post-deployment for bug fixes on Critical and High-priority issues, and technical support for deployment problems.

Archive Location: University project repository + GitHub (7-year retention per academic requirements).

Support Transition: All known issues will be documented with workarounds. Contact information for escalation will be provided to the university IT team.

4. Quality Standards

This project adheres to the ISO/IEC 29110 standard for Very Small Entities (VSE), which defines processes for small teams to achieve quality software delivery. Quality is embedded throughout the project lifecycle — not tested in at the end.

4.1 Applicable Standards and Frameworks

ISO/IEC 29110 focuses on two main processes for this project:

Project Management (PM) Process: Planning, Assessment and Control, and Project Closure.

Software Implementation (SI) Process: Software Requirements Analysis, Software Architecture and Detailed Design, Software Construction, and Software Testing.

Additional standards applied:

| Standard | Application in This Project |
| --- | --- |
| ISO/IEC 25010:2011 — SQuaRE | Quality model for defining quality attributes: functional correctness, performance efficiency, security, reliability, maintainability, and usability. |
| IEEE 829 — Test Documentation | Structure and content of test plans, test records, and test reports. |
| ISO/IEC 29119 — Software Testing | Software testing processes and documentation standards. |
| OWASP Top 10 | Security risk framework applied to authentication, API design, and data handling. |
| IEEE 1058 — Software Project Management Plans | Structure and content requirements for this Project Management Plan document. |
| ISO 31000 — Risk Management | Risk identification, analysis, evaluation, and treatment framework applied in Section 3.5. |

4.2 Quality Objectives and Metrics

| Quality Attribute | Metric | Target | Measurement Method |
| --- | --- | --- | --- |
| Functional Completeness | Requirements coverage | 100% Must-Have | Traceability matrix — every requirement traced to at least one test case |
| Code Quality | Test coverage | > 80% (critical) | pytest-cov (Python) and Jest coverage (JavaScript/TypeScript) |
| Code Quality | Cyclomatic complexity | < 10 per function | Static analysis tools (SonarQube, radon) |
| Performance | API response time | < 500ms (P95) | Load testing with locust or k6 |
| Performance | Code analysis time | < 60s for repos < 50K LOC | Automated timing in test suite |
| Security | Vulnerability count | 0 Critical, 0 High | OWASP ZAP automated scan + Snyk dependency scanning |
| Reliability | System uptime | > 99.5% | Monitoring dashboard (DataDog) tracking availability |
| Usability | User satisfaction score | > 4.0 / 5.0 | Post-deployment survey (5-point Likert scale) |
| Documentation | API documentation coverage | 100% of public APIs | OpenAPI spec validator; automated doc generation check |

4.3 Quality Assurance (QA) Activities

QA activities are proactive — they prevent defects by ensuring processes are followed correctly.

| Activity | Frequency | Responsible Party | Deliverable |
| --- | --- | --- | --- |
| Requirements Review | Once per phase | Project Manager + Sponsor | Requirements review report with sign-off |
| Design Review | Once per phase | Project Manager + Sponsor | Design review report with sign-off |
| Code Review | Per pull request | Developer (self-review for solo project) | Code review checklist completed |
| Static Code Analysis | Per commit (automated) | CI/CD pipeline (automated) | Analysis report in CI dashboard |
| Security Scanning | Weekly (automated) | DevOps Engineer | Security scan report |
| Performance Testing | Per milestone | QA Engineer | Performance test report with P95 timings |
| Documentation Review | Per deliverable | Project Manager | Documentation completeness checklist |
| Internal Quality Audit | End of each phase | PM (self-audit) + Sponsor | Audit report with findings and corrective actions |

4.4 Quality Control — Code Quality Gates

The following automated gates are enforced via the CI/CD pipeline. Code cannot be merged to the main branch without passing all gates:

All unit tests must pass (100% pass rate required)

Code coverage must be >80% for newly added or modified code

No Critical or High-severity security vulnerabilities detected by Snyk

Linting passes: PEP 8 compliance for Python; ESLint for JavaScript/TypeScript

Cyclomatic complexity per function must be <10 (flagged by SonarQube)

4.5 Defect Management

Defects found during testing follow this lifecycle: Identification → Logging (with severity and priority) → Triage (PM assigns to developer) → Resolution (developer fixes) → Verification (QA confirms fix) → Closure.

Severity levels (what kind of problem it is):

Critical: System crash, data loss, security breach — fix immediately

High: Major functionality broken with no workaround — fix in current sprint

Medium: Functionality impaired but workaround exists — fix in next sprint

Low: Minor issue, cosmetic problem — fix when time permits

Priority levels (how urgently it must be fixed):

P0: Fix within 24 hours — production outages only

P1: Fix within current sprint — critical and high defects

P2: Fix in next sprint — medium defects

P3: Fix when time permits — low priority cosmetic issues

5. Software Configuration Management

Software Configuration Management (SCM) defines the rules for naming, storing, versioning, and controlling all project artifacts — both documents and source code. Consistent SCM practices ensure that the team always works with the correct version of each artifact and that changes are traceable.

5.1 Naming Conventions

All project files must follow this naming format:

[ProjectName]-[DocumentName]_v[Version].[Extension]

Where:

[ProjectName] = AIReviewer (consistent short name for the project)

[DocumentName] = Short descriptive name without spaces (use CamelCase or hyphens)

_v[Version] = Version number in X.Y format (e.g., v1.0, v2.1)

[Extension] = File extension appropriate to the file type (docx, pdf, py, jsx, etc.)

Examples:

AIReviewer-ProjectPlan_v2.0.docx

AIReviewer-SRS_v1.0.docx

AIReviewer-TestPlan_v1.0.docx

AIReviewer-SDD_v1.0.docx

Version numbering rules:

Major version (X.0): Significant change requiring stakeholder review and approval — e.g., v1.0 to v2.0

Minor version (X.Y): Small updates, corrections, or internal revisions — e.g., v1.0 to v1.1

Version 0.x is used for drafts under review that have not yet received formal approval

5.2 Project Repository

| Repository Type | Details |
| --- | --- |
| Source Code Version Control | GitHub — stores all source code with full commit history, branch management, and CI/CD pipelines. Repository: github.com/bxzhang/ai-based-reviewer |
| Document Storage | Google Drive — organized folder structure for all project documents. Access controlled by role: Public (user docs), Internal (project management), Confidential (budget, stakeholder analysis). |
| Backup Strategy | Code: GitHub cloud storage (automatic). Documents: Google Drive cloud storage (automatic). Additional backup: local copy on development machine, updated weekly. |
| Access Control | GitHub: Project Manager (owner), Project Sponsor (read access). Google Drive: Project Manager (editor), Project Sponsor (editor for project docs), University Administration (view-only for milestone reports). |

5.3 Branch Strategy (Source Code)

main: Production-ready code only. Protected branch — direct commits not allowed.

develop: Integration branch. All feature branches are merged here first.

feature/[feature-name]: Individual feature development. Merged to develop via Pull Request after code review.

release/[version]: Release preparation branch. Merged to main when ready for deployment.

hotfix/[description]: Emergency fixes for production. Merged directly to main and back-ported to develop.

5.4 Document Control

Every formal project document must include:

Document title and version number on the cover page

Document history table listing all versions, dates, authors, reviewers, and summary of changes

Status indicator: Draft / Under Review / Approved / Superseded

Classification: Internal Use / Confidential / Public

Retention period: 7 years (per academic project requirements)

6. Project Schedule and Milestones

6.1 Detailed Project Schedule by Phase

| Phase | Start | End | Duration | Key Activities |
| --- | --- | --- | --- | --- |
| Phase 1: Initiation | Week 1 | Week 2 | 2 weeks | Project charter, stakeholder analysis, risk register, development environment setup |
| Phase 2: Requirements | Week 3 | Week 6 | 4 weeks | User Requirements Specification, SRS, NFR, use cases, acceptance criteria |
| Phase 3: Design | Week 7 | Week 8 | 2 weeks | System architecture, database schema, API design, security design, UI/UX wireframes |
| Phase 4: Development | Week 9 | Week 16 | 8 weeks | Backend API, authentication, GitHub integration, AST parser, LLM integration, graph analysis engine, frontend UI, visualization dashboard |
| Phase 5: Testing & QA | Week 17 | Week 20 | 4 weeks | Unit testing, integration testing, system testing, security testing, performance testing, user acceptance testing |
| Phase 6: Deployment | Week 21 | Week 22 | 2 weeks | Infrastructure provisioning, staging deployment, production deployment, user and API documentation, operations guide |
| Phase 7: Closure | Week 23 | Week 24 | 2 weeks | Final validation, stakeholder acceptance sign-off, knowledge transfer, lessons learned, project archive, final report |

6.2 Major Milestones and Go/No-Go Criteria

Each milestone represents a significant checkpoint. A formal Go/No-Go decision is made before proceeding to the next phase. The Project Manager and Project Sponsor must both agree on the Go/No-Go decision based on whether all success criteria are met.

| Milestone | Timing & Deliverables | Success Criteria (must all be met) | Go/No-Go Decision |
| --- | --- | --- | --- |
| M1: Project Kickoff | End of Week 1 Project charter, team onboarded, environment ready | Charter approved by Sponsor; development tools installed and verified | GO: Proceed to requirements gathering NO-GO: Resolve setup blockers before starting |
| M2: Requirements Baseline | End of Week 6 SRS, URS, NFR documents | 100% of requirements documented; stakeholder sign-off obtained; all Must-Have requirements clearly defined and measurable | GO: Proceed to system design NO-GO: Complete missing requirements before design begins |
| M3: Design Complete | End of Week 8 SDD, database schema, API specs | Design review passed; all design decisions trace to SRS requirements; architecture approved by Sponsor | GO: Proceed to development NO-GO: Revise design to address review findings |
| M4: Core Features Complete | End of Week 12 Auth system, GitHub integration, AST parser | Unit tests pass with >80% coverage; integration tests pass; all three core backend components functional end-to-end | GO: Proceed to advanced feature development NO-GO: Fix failing tests and integration issues first |
| M5: All Features Complete | End of Week 16 Full backend + frontend + all integrations | All Must-Have functional requirements implemented; system integration tests pass; UI functional and responsive | GO: Proceed to full QA testing phase NO-GO: Complete remaining features and fix integration failures |
| M6: Testing Complete | End of Week 20 Test plan, test records, defect log | All Critical and High-priority defects resolved; NFRs validated (performance, security, uptime); code coverage >80% | GO: Proceed to production deployment NO-GO: Resolve remaining critical defects and re-test |
| M7: Production Deployment | End of Week 22 Live system, full documentation | Staging environment validated; production deployment successful; system accessible to target users; all documentation complete | GO: Proceed to project closure NO-GO: Diagnose and fix deployment failures; re-deploy |
| M8: Project Closure | End of Week 24 Final report, lessons learned, handover | All deliverables accepted by Project Sponsor; final presentation approved; lessons learned documented; project archived | PROJECT COMPLETE: All obligations fulfilled; project formally closed |

6.3 Resource Acquisition Timeline

| Resource | Acquisition Date | Start Use | End Use | Notes |
| --- | --- | --- | --- | --- |
| Development Environment (local machines) | Week 1 | Week 1 | Week 24 | Already available; no acquisition cost |
| LLM API Keys (GPT-4, Claude) | Week 1 | Week 13 | Week 24 | Obtain early for integration testing setup |
| AWS Staging Environment | Week 8 | Week 9 | Week 24 | Provisioned during design phase |
| Neo4j AuraDB | Week 8 | Week 9 | Week 24 | Free trial period, then paid subscription |
| AWS Production Environment | Week 20 | Week 21 | Week 24 | Provisioned just before deployment |
| DataDog Monitoring | Week 20 | Week 21 | Week 24 | Set up alongside production deployment |

6.4 Budget Summary

| Cost Category | Estimated Cost | % of Total Budget |
| --- | --- | --- |
| Personnel (development, QA, PM, DevOps, advisor) | $36,750 | 56.8% |
| LLM API Usage (GPT-4 + Claude, 6 months) | $8,000 | 12.4% |
| Cloud Infrastructure (AWS staging + production) | $2,320 | 3.6% |
| Neo4j AuraDB (6 months) | $520 | 0.8% |
| Development Tools & Training | $3,000 | 4.6% |
| Contingency Reserve (20%) | $10,258 | 15.9% |
| Management Reserve (5%) | $3,077 | 4.8% |
| TOTAL PROJECT BUDGET | $63,925 | 100% |

Note: Personnel costs are estimated based on academic project context and represent the value of time contributed. Actual cash expenditure is significantly lower as BaiXuan Zhang contributes all roles voluntarily as part of the academic project requirement.

Appendix A: Acronyms and Definitions

| Acronym | Definition |
| --- | --- |
| API | Application Programming Interface — a defined set of rules that allows software applications to communicate with each other. |
| AST | Abstract Syntax Tree — a tree representation of the structure of source code that makes it analyzable by programs. |
| AWS | Amazon Web Services — the cloud computing platform used for hosting the system. |
| CCB | Change Control Board — the governance body that reviews and approves or rejects change requests. |
| CI/CD | Continuous Integration/Continuous Deployment — automated pipelines for testing and deploying code. |
| CPI | Cost Performance Index — EVM metric measuring cost efficiency (EV ÷ AC). Values >1.0 mean under budget. |
| CR | Change Request — a formal document requesting a change to project scope, schedule, budget, or quality. |
| EVM | Earned Value Management — a project control methodology that measures schedule and cost performance objectively. |
| JWT | JSON Web Token — a compact, self-contained token used for secure authentication between client and server. |
| KPI | Key Performance Indicator — a measurable metric used to evaluate project or system performance. |
| LLM | Large Language Model — an AI model (e.g., GPT-4, Claude) capable of generating human-like text from context. |
| NFR | Non-Functional Requirement — requirements specifying how a system performs (speed, security, reliability) rather than what it does. |
| PMP | Project Management Plan — this document; the authoritative guide for project governance. |
| PR | Pull Request — a GitHub mechanism for proposing, reviewing, and merging code changes. |
| RACI | Responsible, Accountable, Consulted, Informed — a responsibility assignment matrix. |
| RBAC | Role-Based Access Control — a security model where access permissions are assigned based on user roles. |
| SaaS | Software as a Service — software delivered via the internet without local installation. |
| SDD | Software Design Document — describes the technical architecture and design decisions. |
| SDLC | Software Development Life Cycle — the structured process for developing software from concept to delivery. |
| SPI | Schedule Performance Index — EVM metric measuring schedule efficiency (EV ÷ PV). Values >1.0 mean ahead of schedule. |
| SRS | Software Requirements Specification — the document defining what the system must do. |
| URS | User Requirements Specification — the document capturing user needs in business language. |
| VSE | Very Small Entity — an organization with up to 25 people (ISO/IEC 29110 context). |
| WBS | Work Breakdown Structure — a hierarchical decomposition of all project work into manageable packages. |

Appendix B: References

ISO/IEC 29110-4-1:2018 — Software engineering: Lifecycle profiles for Very Small Entities (VSEs).

IEEE Std 1058-1998 — IEEE Standard for Software Project Management Plans.

ISO 21500:2012 — Guidance on project management.

ISO/IEC/IEEE 29148:2018 — Systems and software engineering: Life cycle processes — Requirements engineering.

ISO/IEC 25010:2011 — Systems and software Quality Requirements and Evaluation (SQuaRE).

IEEE 829:2008 — Standard for Software and System Test Documentation.

ISO 31000:2018 — Risk management — Guidelines.

OWASP Top 10 (2021) — Top 10 Web Application Security Risks. https://owasp.org/Top10

Project Management Body of Knowledge (PMBOK) Guide, 7th Edition. Project Management Institute.

Agile Practice Guide, Project Management Institute (2017).

Appendix C: Document Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared By | BaiXuan Zhang | _______________________ | __________ |
| Reviewed By | Dr. Siraprapa Wattanakul | _______________________ | __________ |
| Approved By | Dr. Siraprapa Wattanakul | _______________________ | __________ |